## Budget
Housing solutions project - pilot project sample budget (Year 1-3) |  |  | Budget: Project Expenses | [15 empty] | Budget: Annual Staff Costs (FTE equivalent) |  |  | Total Project Costs |  |  | Annual Cashflow |  |  | Work Planning (by week)
| # sessions | # people | participant honorarium (2 hrs) | workshop supplies | workshop refreshments | hotel/night | mileage | printing | Advertising | Office space (monthly) | Monthly cell phone | Computer+workstation equipment | facility/room/booth rental | Speaker/trainer | Legal fees / professional services fees (hrly) | ASL/translation | Elder | Other (misc. costs) | Project Coordinator | Project supervisor | blank (add other positions as relevant) | PROJECT EXPENSES | STAFF COSTS | TOTAL | Year 1 | Year 2 | Year 3 | [53 empty] | Q1 Year 2 | Q2 Year 2 | Q3 Year 2 | Q4 Year 2 | Q1 Year 3 | Q2 Year 3 | Q3 Year 3 | Q4 Year 3 | time axis 2024-06-01 to 2025-05-31
Rates --> |  |  | 100 | 1 | 20 | 200 | 0.65 | 1.5 | 1 | 1500 | 75 | 4500 | 500 | 800 | 200 | 300 | 300 | 1 | 93184 | 105000
Project activities
Project Set Up | [21 empty] | 24300 | 57092 | 81392 | 81392 | 0 | 0
Staffing costs
Staff time | 6 |  | n/a | n/a | n/a | [13 empty] | 0.5 | 0.1 |  | 0 | 57092 | 57092 | 57092 | 0 | 0 | bar: 2024-06-01 to 2024-11-09
Hiring + office + client meeting space | 6 |  | n/a | n/a | n/a |  |  |  |  | 6 | 12 | 1 | [5 empty] | 150 |  |  |  | 14550 | 0 | 14550 | 14550 | 0 | 0 | bar: 2024-06-01 to 2024-06-22
Mandatory staff training | 6 |  | n/a | n/a | n/a | [12 empty] | 400 |  |  |  | 400 | 0 | 400 | 400 | 0 | 0 | bar: 2024-06-15 to 2024-06-29
Program materials + promotion
Program licensing fee for course content (e.g. JIBC course) |  |  | n/a | n/a | n/a | [12 empty] | 800 |  |  |  | 800 | 0 | 800 | 800 | 0 | 0 | bar: 2024-06-29 to 2024-07-20
Set up policies + procedures + training modules |  |  | n/a | n/a | n/a | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2024-06-29 to 2024-07-20
Set up contracts and agreement templates |  |  | n/a | n/a | n/a | [9 empty] | 4 | [6 empty] | 800 | 0 | 800 | 800 | 0 | 0 | bar: 2024-07-13 to 2024-08-03
Program promotional and education materials (incl comms design + videos) |  |  | n/a | n/a | n/a |  |  | 500 | 1000 | [8 empty] | 5000 |  |  |  | 6750 | 0 | 6750 | 6750 | 0 | 0 | bar: 2024-08-10 to 2024-08-31
Recruitment events (e.g. booth at seniors fair, social media, newspaper + print ads) |  |  | n/a | n/a | n/a |  |  |  | 500 |  |  |  | 1 | [8 empty] | 1000 | 0 | 1000 | 1000 | 0 | 0 | bar: 2024-09-07 to 2024-11-09
Project Implementation | [21 empty] | 73462.5 | 0 | 73462.5 | 61075.8333 | 6193.3333 | 6193.3333
Staffing costs
Staff time | 30 |  | n/a | n/a | n/a | [13 empty] | 2.5 | 0.25 |  | 0 | 259210 | 259210 | 51842 | 103684 | 103684 | [53 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2024-11-16 to 2025-05-31
Hiring + office + client meeting space | 30 |  | n/a | n/a | n/a |  |  |  |  | 30 | 12 | 1 | [5 empty] | 750 |  |  |  | 51150 | 0 | 51150 | 10230 | 20460 | 20460
Mandatory staff training | 30 |  | n/a | n/a | n/a | [12 empty] | 2000 |  |  |  | 2000 | 0 | 2000 | 400 | 800 | 800 | [53 empty] | 1 |  |  |  | 1
Participant matching
Intake survey + interviews |  |  | n/a | n/a | n/a |  |  | 50 | [13 empty] | 75 | 0 | 75 | 75 | 0 | 0 | bar: 2024-11-16 to 2024-11-30
Initial home visits / assessments / neighbourhood visits | 1 | 5 | 0 | 0 | 0 |  | 150 | 20 | [13 empty] | 127.5 | 0 | 127.5 | 127.5 | 0 | 0 | bar: 2024-11-30 to 2024-12-21
Participant background checks & references | 1 | 20 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2024-11-30 to 2024-12-21
Meet and greet between matches | 2 | 20 | 0 | 40 | 800 | [7 empty] | 2 | [8 empty] | 17040 | 0 | 17040 | 17040 | 0 | 0 | bar: 2024-12-28
Participant agreements | 1 | 20 | [5 empty] | 20 | [13 empty] | 30 | 0 | 30 | 30 | 0 | 0 | bar: 2025-01-04 to 2025-01-11
Legal fees for reviewing/administrating tenancy/homeshare contracts/agreements | 1 | 5 | 0 | 5 | 100 | [9 empty] | 5 | [6 empty] | 3005 | 0 | 3005 | 3005 | 0 | 0 | bar: 2025-01-04 to 2025-01-11
Participant training - Financial supports options | 1 | 20 | 0 | 20 | 400 | [7 empty] | 1 | 1 | [7 empty] | 9320 | 0 | 9320 | 9320 | 0 | 0 | bar: 2025-01-11
Participant training - General orientation | 1 | 20 | 0 | 20 | 400 | [7 empty] | 1 | [8 empty] | 8520 | 0 | 8520 | 8520 | 0 | 0 | bar: 2025-01-18
Participant training - Right & responsibilities | 1 | 20 | 0 | 20 | 400 | [7 empty] | 1 | 1 | [7 empty] | 9320 | 0 | 9320 | 9320 | 0 | 0 | bar: 2025-01-25
Participant training - communication & conflict skills | 1 | 20 | 0 | 20 | 400 | [7 empty] | 1 | 1 | [7 empty] | 9320 | 0 | 9320 | 9320 | 0 | 0 | bar: 2025-02-01
Check-ins & Ongoing support
Participant check-ins (at service provider office) | 30 |  | n/a | n/a | n/a |  | 4500 | [7 empty] | 6 |  |  | 5250 |  |  |  | 9375 | 0 | 9375 | 1875 | 3750 | 3750 | [53 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2025-02-08 to 2025-05-31
Ongoing coordinator support |  |  | n/a | n/a | n/a | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2025-02-08 to 2025-05-31
Contingency / Emergency supports
Hotel for emergency situations |  |  | n/a | n/a | n/a | 14 |  | 20 | [13 empty] | 2830 | 0 | 2830 | 943.3333 | 943.3333 | 943.3333 | [53 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2025-05-24 to 2025-05-31
Emergency mediation support or referrals |  |  | n/a | n/a | n/a | [7 empty] | 3 |  | 15 | [6 empty] | 4500 | 0 | 4500 | 1500 | 1500 | 1500 | [53 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: 2025-05-24 to 2025-05-31
Program monitoring & evaluation | [21 empty] | 10562.5 | 0 | 10562.5 | 3520.8333 | 3520.8333 | 3520.8333
Staff evaluation (internal) |  |  | n/a | n/a | n/a | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [55 empty] | 1 |  |  | 1 |  | 1 | bar: 2025-02-08 to 2025-02-15; 2025-05-24 to 2025-05-31
Program revisions & adjustments (e.g. for next cohort) |  |  | n/a | n/a | n/a | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [58 empty] | 1 |  | 1 | bar: 2025-02-22 to 2025-03-01; 2025-05-24 to 2025-05-31
Participant evaluations (survey + focus group discussion) | 1 | 25 | 0 | 25 | 500 |  |  | 25 |  |  |  |  | 1 | [8 empty] | 10562.5 | 0 | 10562.5 | 3520.8333 | 3520.8333 | 3520.8333 | [56 empty] | 1 |  |  |  | 1 | bar: 2025-05-31
Subtotal Units |  |  | 0 | 150 | 3000 | 14 | 4650 | 635 | 1500 | 36 | 24 | 2 | 11 | 3 | 30 | 0 | 0 | 14350 | 3 | 0.35 | 0
Subtotal cost |  |  | 0 | 150 | 60000 | 2800 | 3022.5 | 952.5 | 1500 | 54000 | 1800 | 9000 | 5500 | 2400 | 6000 | 0 | 0 | 14350 | 279552 | 36750 | 0 | 161475 | 316302 | 477777 | 208460.6667 | 134658.1667 | 134658.1667
Project management
Organization admin |  |  | 0 | 27 | 10800 | 504 | 544.05 | 171.45 | 270 | 9720 | 324 | 1620 | 990 | 432 | 1080 | 0 | 0 | 2583 | 50319.36 | 6615 | 0 | 29065.5 | 56934.36 | 85999.86 | 37522.92 | 24238.47 | 24238.47
Subtotal cost |  |  | 0 | 27 | 10800 | 504 | 544.05 | 171.45 | 270 | 9720 | 324 | 1620 | 990 | 432 | 1080 | 0 | 0 | 2583 | 50319.36 | 6615 | 0 | 29065.5 | 56934.36 | 85999.86 | 37522.92 | 24238.47 | 24238.47
Total Fees |  |  | 0 | 177 | 70800 | 3304 | 3566.55 | 1123.95 | 1770 | 63720 | 2124 | 10620 | 6490 | 2832 | 7080 | 0 | 0 | 16933 | 329871.36 | 43365 | 0 | 190540.5 | 373236.36 | 563776.86 | 245983.5867 | 158896.6367 | 158896.6367
Note on AF3: Instructions: Change initial date to project start date. All other weeks will update.
Note on U4: $35/hr X 40 hrs/week X 52 weeks + 28% MERCS (benefits)
Note on AF8: Instructions - Add a "1" or any text to each box and it will fill in blue. You can use this to help plan your timelines and activities for your project. You could use numbers to indicate effort level (e.g. time required in days or hours)
Note on B9: 6 months setup
Note on U9: assumes 1 year of salary - project coordinator working 1.0 FTE =1.0FTE x 36 months / 12 months per year
Note on V9: Assumes 0.2 FTE of time for supervisor per year to oversee coordinator and program launch
Note on B10: 6 months setup
Note on S10: software expenses of $300/yr x 36 months / 12 months per year
Note on B11: 6 months setup
Note on S16: professional comms design / video production
Note on B20: 30 months program implementation
Note on U20: assumes 1 year of salary - project coordinator working 1.0 FTE =1.0FTE x 36 months / 12 months per year
Note on V20: Assumes 0.1 FTE of time for supervisor per year to oversee coordinator
Note on B21: # program months
Note on S21: software expenses of $300/yr x 36 months / 12 months per year
Note on H25: assume 12 homes x 25km per home visit/assessment
Note on S26: assume participant pays for criminal receord check
Note on C30: assume 2 homeproviders + 2 homeseekers per unit
Note on B35: months of program
Note on S35: monthly insurance for home visits

## Acknowledgements
Published by Simon Fraser University (SFU) Renewable Cities, a program of the SFU Morris J. Wosk Centre for Dialogue, 2024.
This spreadsheet is offered under the Creative Commons Attribution-NonCommercial-ShareAlike 4.0 License, enabling free sharing and reprinting for non-profit and non-commercial purposes with attribution.
The Seniors Hidden Housing Solutions to Affordability and Climate Change received funding from Canada Mortgage and Housing Corporation (CMHC) under the NHS Solutions Labs, however, the views expressed are the personal views of the author and CMHC accepts no responsibility for them.
Seniors Hidden Housing Solutions to Affordability and Climate Change a reçu du financement de la Société canadienne d'hypothèques et de logement (SCHL) en vertu du les laboratoires des solutions de la SNL Cependant, les opinions exprimées sont les opinions personnelles de l'auteur et la SCHL n'accepte aucune responsabilité à l'égard de telles opinions. "
Additional funding received from Vancity.